## Slide 1: The Dellingr Challenge: from Conception to Operations Systems Engineering Seminar
Charles Clagett (Charles.E.Clagett@nasa.gov)
Luis Santos (Luis.H.Santos@nasa.gov)

## Slide 2: Agenda
Project Formulation
Mission Design
  Baseline design
  Design maturation
Integration and Testing
  Approach
  Challenges
Operations
  Challenges
  Status
Closing Remarks
Lessons learned addressed in each section

## Slide 3: Project Formulation – Goals
The Center recognized the importance of SmallSats and wanted to investigate in particular what really takes to develop a CubeSat mission
  At the time, it was said universities can do it very quickly and cheaply (<1 year, <$1M)
  GSFC formulation for mission proposals utilizes typical processes, making these projects unwinnable
  Utilizing HQ resources and IRAD funding to gain much needed experience with the marketplace COTS components and development of a Cubesat
Effort Objectives
  For GSFC to develop an understanding of the current state of practice with respect to the capabilities of CubeSat-class platforms to host meaningful science missions
  To show, by undertaking a hands-on developmental activity (Dellingr Mission), a path forward toward enhancing technological capability to accomplish more formidable scientific missions with CubeSats
Dellingr Mission objective
  Define and develop a mission to conduct a heliophysics science investigation utilizing two, three or four science payloads already in development at GSFC
  Design, build, test, and flight qualify a 6U CubeSat within a one-year time period

## Slide 4: Project Formulation – Plan
Original objectives were selected to stress the typical Goddard project and engineering approach
Initial Spacecraft Bus budget: 3.2 FTEs, $100k based on university cost claims, instruments cost not part of the budget
Only 2 full-time members (PM and DPM)
  Positions were posted, applicants interviewed and selections made
    Position 1: Project Manager, Systems Engineer, Procurements, I&T, etc.
    Position 2: Deputy Project Manager, Mission Systems Engineer, I&T, etc.
  Part-time staff to provide support as needed
Timeline of 1 year
Do no harm risk classification

## Slide 5: Project Formulation – Plan
Met with 670 personnel and created a list of payloads in development
Three (3) payloads were selected based on maturity and size
  Science Magnetometers (DAGR)
  Ion Neutral Mass Spectrometer (INMS)
  Compact Relativistic Electron Proton Telescope (CREPT)
Launch opportunity was not defined
  An actual launch manifest took years after this point
  It was later decided to baseline an ISS orbit due to the availability of such launches, this orbit removed CREPT

## Slide 6: Project Formulation – Initial Organization Chart
Michael Hesse
Heliophysics Division
Michael Johnson
ETD
Nick Paschalidis
Instruments Manager
Chuck Clagett
Project Manager
Luis Santos
Deputy PM
INMS
N. Paschalidis (PI)
S. Jones (CoI)
M. Rodriquez (LE)
Boom Mag
L. Kepko (PI)
G. Le (CoI)
T. Bonalsky (LE)
Internal Mag
E. Zesta (PI)
T. Bonalsky (LE)
CREPT
S. Kanekal (PI)
T. Jamison (LE)
Luis Santos
Systems, Mechanical,
Structure
Scott Hesh
Power, Comm,
Custom Card
Scott Starin
GN&C
Salman Sheikh
C&DH, Harness, Software
Chuck Clagett
Systems, Thermal
Aprille Ericsson
Technology Manager
Dellingr Funding
Other
Funding

## Slide 7: Project Formulation – Initial Key Philosophies
Minimize paperwork – learn through experience which documentation is vital to drive the project
Streamline reviews
Only apply GSFC processes if critical (no mandatory compliance with NPRs, GPRs and GOLD rules)
Science requirements are negotiable
Design, Build, Test and Fix – Minimize analysis work and focus on system level testing
Use part-time help as needed only
Reliance on subsystem leads
Use ”CubeSat Market” components as much as possible as part of the tech demo
No spare flight hardware or flatsat

## Slide 8: Project Formulation – Name
First great team challenge of Dellingr mission, its name
Originally referred to as the “skunkworks” project
Received “cease and desist” letter from Lockheed Martin for the “skunkworks” name
Process took many iterations and conversations
Many acronyms suggested and kept one in place until a name was defined
  HeiSt-1 (Heliophysics Satellite 1)
  Seem fitting since we were taking any free leftovers hardware we could locate like solar cells, GPS card, reaction wheels, etc.
Finally settled on Dellingr
  Wanted to use name instead of acronym
  Dellingr is the Norse god of “Dawn”
  It represents “Dawn of Cubesats” at GSFC
  Credit for name suggestion to Larry Kepko

## Slide 9: Mission Design – Initial Key Parameters
Operate for a minimum of 3 months
Operate successfully 3 GSFC instruments for at least 3 consecutive orbits
  Ram pointing for INMS
  No specific pointing for DAGR
ISS-like orbit (400km, 51.65 deg inclination, 93 minutes)
Use the Planetary System Corporation (PSC) 6U standard
Other key parameters based on CubeSat experience at the time
  Use a beacon to locate satellite upon ejection
  Use 30-minute and 45-minute timers for deployments and transmissions respectively
  Keep batteries at 20% depth of discharge or smaller
  Use 3 separation switches
  Have software capability to update from the ground

## Slide 10: Mission Design– Initial Baseline Approach
Budget and schedule are very aggressive, reuse was viewed as key for success
  Leverage and reuse components from other efforts and missions
  Use proven cubesat market components
  At the time, it was advertised as almost “plug-and-play” utilizing the PC104 CubeSatKit Bus standard
Original plan:

## Slide 11: Mission Design– Final General Sequence

## Slide 12: Mission Design – In-House vs. Out-of-house
Cards Stack
PC/104 Backplane
Science Mags
MEMs Gyro X4
I2C, +5V
RS232,+3.3V
+5.0V, +8.0V
Clyde Space Batteries X3 (90Wh)
RS232
+3.3V
SPI
+3.3V
+8V
+8V
Torquer, FSS, CSS SPI, +5V
Torquer, CSS
SPI, +3.3V, +/-5.0V
INMS
Balun, capacitors, etc.
GPS Antenna
Boom Rel. Mech., 3.3V
Mags Power and Data
L3 Cadet
Wheel
4x UHF Antenna
Panel
Panel
Panel
Sep Switch
RBF Switch
Boom Mag and Billingsley Mags
2x 3U
2x 6U
2x 2U
3x
3x
Torquer, FSS,
SPI, +5V
Clyde Space EPS
+8V
GomSpace NanoMind
GPS Card
Antenna Rel. Mech., 3.3V
Special Services Card
In-House
Market Component

## Slide 13: Mission Design – Why In-House?
Solar Panels
  With the allocated budget, solar panels were very expensive
  Learned from Aerospace Corp. an inexpesive way to make solar panels using PCBs as substrate
  Used left-over ZTJ solar cells from GPM
  Decided to used body mounted solar panels (instead of deployables) to simplify the development and minimize procurement cost
Torquers
  Since solar panels will be done in-house, we can embed traces in a loop to effectively create a torquer with no residual field since it doesn’t have a core
Science magnetometer boom (could not find a good boom from the market)
Fine Sun Sensor
  Leveraged the IRAD investment in a fine sun sensor developed by WFF
GPS antenna
  Decided to use GPS antenna from the FireFly cubesat (smallest we can find)
  Vendor did not make the antenna anymore but provided documentation necessary to build it ourselves

## Slide 14: Mission Design – Why In-House?
Special Services Card
  Since most components are “off-the-shelf”, the SSC provides any connectivity and functionality lacking on purchased components (additional voltages, additional switches, fuses, IO expanders, etc.)
UHF Antenna
  Could not find a reliable/proven UHF antenna product from a vendor
Release Mechanism (boom and antenna)
  Leveraged the IRAD investment in a miniaturized release mechanism developed by WFF
Software
  Decided to use the in-house core Flight Software to minimize software development
  Decided to develop ACS algorithms in-house
Mix of previous efforts and mission left-overs and in-house developments reduced initial hardware procurement cost from ~$300k to ~$125k

## Slide 15: Mission Design – Final Concept of Operations
Command
(anomaly assessed)
Charging Mode
1- Off (inside deployer)
Charging Mode
INMS Mode
Data Link (after timer expires)
Data Link
RTS or Anomaly
(1 full orbit with INMS)
Data Link
Commission (Ground Command)
Dagr Mode
Data Link
RTS
(After predetermined amount of charging orbits)
If Anomaly
2- Sep Sws Activate Sat + Timer “On”
5- Bus and Payloads Checks/Tests
4- Deployments and Health Status
3- Timer Completed
RTS or Anomaly
(1 full orbit with Dagr)
RTS
(After predetermined amount of charging orbits)
Safe Mode
Data Link

## Slide 16: Mission Design – Initial Concept (Outside)
INMS
Coarse Sun Sensor
CREPT
GPM Solar Cells
TASC Solar Cells
Fine Sun Sensor
Temp Sensor
GPM Solar Cells
Temp Sensor
Coarse Sun Sensor
Separation Switches
Coarse Sun Sensor
Temp Sensor
EGSE & RBF
Base Plate

## Slide 17: Mission Design – Initial Concept (Inside)
L3 Cadet
3X Science Magnetometer
3X Reaction Wheels
CREPT
INMS
Mag Boom
Science Mag Card
Dellingr Custom Card
GomSpace NanoMind
Clyde Space Batteries
Clyde Space EPS
Separation Switches

## Slide 18: Mission Design – Update 1
Higher fidelity model:
  Higher-gain circularly-polarized UHF antenna
  GPS antenna
Simplified boom (flip vs. slide)
Eliminated CREPT

## Slide 19: Mission Design – Update 2
Changed boom from single-deploy to a double-deploy system
Added still camera to confirm deployments
Added thermal louver experiment

## Slide 20: Mission Design – Safety Requirements
We heard through 3rd parties that ISS requirements for safety are rigorous
Attempted talking to launch provider directly but will not engage unless manifested
Attempted to talk to JSC directly but we were getting requirements without rationale or information about prior agreements for CubeSats
From these conversations, it was realized the batteries procured were not adequate
  Did not comply with cell level testing required
  Did not comply with the 3 inhibits scheme as defined by them
  Current baseline of 90Wh requires additional, costly testing for thermal runaway (80Wh is the limit)
  Decided to change to 80Wh due to cost and accept operational impact to mission

## Slide 21: Mission Design – Update 3
Added ISS-rated batteries
Changed antenna to a dipole
Added more cells to the 6U face
Added more sensitive MEMs gyro
Added CubeSat market fine sun sensors
Added inhibit bypass feature

## Slide 22: Mission Design – Dellingr Hardware (not all-encompassing)
Special Services Card
Solar Panel
Flight Boom
Fine Sun Sensor
Base plate, card stack, reaction wheels and radio
C&DH Card
EPS Card

## Slide 23: Mission Design – Challenges and Lessons Learned
Obtain launch manifest as soon as possible
  Safety requirements (use ISS safety requirements to reduce design risk)
  CubeSat carrier system requirements
  Launch accommodation capability (purge, cleanliness, etc.)
CubeSat components maturity was not as expected/advertised
  Not “plug-and-play”
  Lack consistent documentation
  Delivered product may differ from the one ordered
Design communication system to work from any orientation
Minimize ground intervention by keeping orbit operations simple
Constantly re-negotiate science requirements to save time and resources

## Slide 24: Integration and Testing – Approach
Non-traditional approach to verification & validation due to necessity
  Limited resources
  Below Class D Mission
  Risk reduction effort related to minimum success criteria
Testing based on ConOps activities
Construct tests to serve multiple purposes
Traceability through TDMS CM system, WOAs, procedures, and ITOS logging
Testing generally deferred to system level except for high risk components
Dellingr inside Handling Fixture

## Slide 25: Integration and Testing – Flow
Signal integrity test
Separation switches testing
Battery heater and inhibit testing for new batteries
Magnetic Checkout @ Magnetic Calibration Facility
Battery low voltage test – spacecraft reset
TVAC Deployment @ Wallops
End-to-End Comm Test @ Wallops
GPS Simulation Test
Successful release but confirmation switch failed
Transmission to Goddard MOC failed
Success
Fail or partial fail
Fix
Functional test (Pre-vibe)
Vibration test 01
Functional test (Post-vibe)
Bakeout

## Slide 26: Integration and Testing – Flow
TVAC
EPS BCR concerns first appeared
Replacement batteries TVAC test
Hi FIFO repaired
Battery telemetry failed
Radio sending data with errors (Hi FIFO overflow)
SSC release mechanism circuit power output
SPI bus communication (DAGR & WFSS stays on)
Diagnostic port failed
DAGR boom temp. sensor stop functioning
Success
Fail or partial fail
Fix
Reworked and tested release mechanism to increase reliability
SSC circuit repaired
New EPS received
SSC deployment circuit testing
Mechanical reassembly
Aliveness test
Deployment test in the Lab
WFSS Fix (update firmware, chip select fix)
Reinstall Dagr, EPS, & SSC to Card Stack
Single-pin harness connections tack-solder (fix Diagnostic port)
Dagr mag head temperature reading fix
Complete reassembly except +Y
Re-arm release mechanisms
Removed EPS (test), SSC & Dagr(rework), solar panels (flash test) and battery swap

## Slide 27: Integration and Testing – Flow
Cadet Radio Testing
30-minute timer test
Functional test and GPS simulation
Day-in-the-life
Ground station pass test
Ambient functional test
Bake-out
Regression TVAC
DAGR power consumption the same on all modes
INMS data with unacceptable amount of errors
DAGR data problem in flight software
GPS not getting powered on during some mode transitions
GPS not communicating with FSW
Constant reboot of spacecraft – I2C errors
NanoRacks fit-check
Vibe Test (NanoRacks)
Post-Environmental Functional Test & GPS Simulation
Magnetic test in the lab – Boom mag broken
Dagr boom mag head reinstalled
Mag sensitivity test at facility
Magnetic characterization and momentum management test
Pre-ship day-in-the-life
Final boom magnetometer calibration
Success
Fail or partial fail
Fix

## Slide 28: Integration and Testing – Delivery and Deployer Integration

## Slide 29: Integration and Testing – Failure Detection and Correction
Philosophy - keep things simple and easy to test
Implementation
  Limit checker and relative time sequences
  Daily reset to simplify FDC development and watch points
Testing - all testing done on flight unit
  Inject undesirable condition, watch system correct itself
  Inject undesirable condition, watch system try to start deployment RTS
  Inject undesirable condition via test code, watch system respond

## Slide 30: Integration and Testing – End of campaign concerns
Boom magnetometer broke during testing with unidentified cause (made mechanical changes)
NanoMind magnetometer bias shifting at random (use boom)
NanoMind resets (unable to recreate problem)
No system-level charging of batteries from solar panels (flash test and BCRs checks performed)
Have experience Cadet radio locking up at random times with unidentified cause (10 min FDC timeout)
Cadet radio overheating during ground pass

## Slide 31: Integration and Testing – Challenges and Lessons Learned
Use a 3D printed model for parallel harness development
Have a full flatsat available with hardware in the loop and a physics simulator
Tailor subsystem-level component testing based on experience and confidence of selected hardware
Do not underestimate effort to produce a CubeSat
  Efforts between large and small spacecraft are analogous in regards to software, communications, ground system, and ACS
  The system still fundamentally needs to perform the same functions with comparable analysis and testing
  Many of the lessons learned are old lessons relearned because basic best practices are universal in application regardless of the size of mission

## Slide 32: Operations – Ground System
TCP/IP
Alternate MOC (ITOS)

## Slide 33: Operations – First Day
Ejected from ISS on November 20, 2017 @ 12:00pm
First contact at 8:00pm

## Slide 34: Operations – Deployment Issue
Deployment and initial checkout
First 74 Hours (battery voltage). Satellite turned on inside deployer at unknown time for 21 hours. Dellingr restored nicely upon ejection.
21 hrs
on inside container
Deployed
Power system working as expected
We observed antenna and boom deploy in real-time
Battery voltage vs. packet #

## Slide 35: Operations – Fine Sun Sensor Issue
Nov. 30, 2017 | Observed anomalous gyro data Observed sun pointing inaccuracy
Pointed at sun
Stressing the wheels
Still pointed at sun
In-House FSS
Vendor FSS
Vendor FSS
In-House FSS
Notes: To this day we still have not figured out the issue. But we can live without the gyro.
the plot on right shows the issue. We have 2 FSS - commercial and in house —
Then on December 19th a real punch to the gut. We lost our GPS. You can see here the moment we think it failed.
Critical loss because w/o GPS we could not maintain ram point mode, which was needed for the mass spec.
The INMS measures ion and neutrals in earth’s upper atmosphere. We haven’t had these measurements since the early 80’s. Validating this instrument, and proving we can make these measurements in a cubesat form factor, is really important for heliphysics and for the future upcoming GDC mission.
We enter January bruised but not beaten, and had a plan to recover mass spectrometer science

## Slide 36: Operations – GPS Issue
Dec. 19, 2017 | GPS unresponsive
Moment GPS failed
GPS
Notes: To this day we still have not figured out the issue. But we can live without the gyro.
the plot on right shows the issue. We have 2 FSS - commercial and in house —
Then on December 19th a real punch to the gut. We lost our GPS. You can see here the moment we think it failed.
Critical loss because w/o GPS we could not maintain ram point mode, which was needed for the mass spec.
The INMS measures ion and neutrals in earth’s upper atmosphere. We haven’t had these measurements since the early 80’s. Validating this instrument, and proving we can make these measurements in a cubesat form factor, is really important for heliphysics and for the future upcoming GDC mission.
We enter January bruised but not beaten, and had a plan to recover mass spectrometer science

## Slide 37: Operations – Resets Issue
CPU having difficulty talking to subsystems
Early January, we started to see a lot of errors on the I2C bus (how the flight computer talks to various subsystems)
By late January, the reset situation had significantly worsened
Notes: But Dellingr had other ideas.
This is a standard 24-hour plot of errors. top panel in red shows the I2c error per telemetry packet. Black lines are CPU resets.
It was also this time that TZ walked into my office. But w/ resets, couldn’t turn on INMS
Spent much of mid January trying to isolate what was causing the issue.

## Slide 38: Operations – Resets Issue
18-031-20:23:04.000000 (2 ) (SC ) ( 73) (RTS Number 001 Started )
18-031-20:23:10.000000 (3 ) (CFE_SB ) ( 17) (Msg Limit Err,MsgId 0x18c2,pipe ACS_CMD_PIPE,sender SCH )
16-122-00:00:12.000000 (2 ) (FM ) (104) (Free Space Table verify results: good entries = 2, bad = 0, unused = 6 )
16-122-00:00:12.000000 (2 ) (FM ) ( 1) (Initialization complete: version 2.3.1.0 )
16-122-00:00:12.000000 (2 ) (FM ) (100) (Child Task initialization complete )
16-122-00:00:12.000000 (3 ) (SC ) (123) (Unbundle RTS OK: /boot/rtsb01.bin, Dest: /ram, RTS Size: 416, RTS Num: 4 )
16-122-00:00:12.000000 (3 ) (SC ) (123) (Unbundle RTS OK: /boot/rtsb02.bin, Dest: /ram, RTS Size: 416, RTS Num: 14 )
16-122-00:00:12.000000 (3 ) (SC ) (123) (Unbundle RTS OK: /boot/rtsb03.bin, Dest: /ram, RTS Size: 416, RTS Num: 16 )
16-122-00:00:13.000000 (3 ) (SC ) (123) (Unbundle RTS OK: /boot/rtsb04.bin, Dest: /ram, RTS Size: 416, RTS Num: 24 )
16-122-00:00:13.000000 (3 ) (SC ) (123) (Unbundle RTS OK: /boot/rtsb05.bin, Dest: /ram, RTS Size: 416, RTS Num: 31 )
16-122-00:00:13.000000 (2 ) (SC ) ( 21) (RTS table file load count = 32 )
16-122-00:00:13.000000 (2 ) (SC ) ( 9) (SC Initialized. Version 2.3.0.0 )
16-122-00:00:13.000000 (2 ) (LC ) ( 56) (WDT verify results: good = 15, bad = 0, unused = 49 )
16-122-00:00:14.000000 (2 ) (LC ) ( 66) (ADT verify results: good = 14, bad = 0, unused = 50 )
16-122-00:00:14.000000 (2 ) (LC ) ( 2) (LC Initialized. Version 0.0.0.0 )
16-122-00:00:16.000000 (2 ) (SEC ) ( 4) (SEC: RESET command )
16-122-00:00:16.000000 (2 ) (SEC ) ( 1) (SEC Initialized. Version 1.0.0.0 )
16-122-00:00:16.000000 (2 ) (FUL ) ( 1) (FUL App Initialized. Version 1.0.0.0 )
16-122-00:00:16.000000 (2 ) (FDL ) ( 1) (FDL App Initialized. Version 1.0.0.0 )
16-122-00:00:16.000000 (2 ) (MM ) ( 1) (MM Initialized. Version 0.0.0.0 )
16-122-00:00:16.000000 (2 ) (CS ) (144) (CS Eeprom Table verification results: good = 8, bad = 0, unused = 8 )
16-122-00:00:16.000000 (2 ) (CS ) (143) (CS Memory Table verification results: good = 0, bad = 0, unused = 16 )
16-122-00:00:16.000000 (2 ) (CS ) (107) (CS Memory Table: No valid entries in the table )
16-122-00:00:16.000000 (2 ) (CS ) (142) (CS Apps Table verification results: good = 0, bad = 0, unused = 24 )
16-122-00:00:17.000000 (2 ) (CS ) (108) (CS Apps Table: No valid entries in the table )
16-122-00:00:17.000000 (2 ) (CS ) (139) (CS Tables Table verification results: good = 46, bad = 0, unused = 26 )
16-122-00:00:17.000000 (2 ) (CS ) ( 1) (CS Initialized. Version 0.0.0.0 )
16-122-00:00:17.000000 (2 ) (MD ) ( 7) (Dwell Tables Recovered: 0, Dwell Tables Initialized: 4 )
18-031-20:24:08.000000 (2 ) (SC ) ( 73) (RTS Number 001 Started )
18-031-20:24:14.000000 (3 ) (CFE_SB ) ( 17) (Msg Limit Err,MsgId 0x18c2,pipe ACS_CMD_PIPE,sender SCH )
16-122-00:00:07.000000 (2 ) (CADET ) ( 1) (L386 CADET: App Initialized using DEFAULTS. Version 1.0.0.0 )
Crash!
Crash!
Reboot
January 26-February 5
January 26, Friday. Last contact with flight computer.
January 29, Monday, windy
January 30, Tuesday, windy
January 31st contact through radio, but couldn’t talk to flight computer
From January 26 - February 5, >13,000 resets. Reboot every 64 seconds, continuously, for 10 days
Notes: 1/26 6127 reset counter
2/5 19832 reset counter
1370 / day - reset every 64 seconds

## Slide 39: Operations – Resets Issue
Satellite C&DH not responding
Radio is responding when talking directly to it
Not clear if resets are occurring due to EPS or C&DH
  Talked to radio with long transmission bursts to see if the EPS was resetting
  No radio resets occurred during experiment, indicating CPU reset only
Radio has a direct IO line to the C&DH CPU for processor reset
Theory:
  C&DH is booting up long enough to service the I2C line
  EPS watchdog used to reset spacecraft is not being triggered
  By enabling IO line for 4 minutes during a pass, the EPS watchdog will not be served and the EPS will perform a system hard reset clearing the problem
  IT WORKED!
Notes: February 6. The mood was dark within the Dellingr team. We were able to reproduce the reboot on the flatsat, traced to driver

## Slide 40: Operations – Science Data!
10 minutes of data during the Feb 6 pass after recovery
“Victory. [WE were] able to turn on INMS in the ION mode. We had no resets between the last pass and this one.”
Notes: Not just on - but on for 18 hours
So back to business. We turn on INMS mode for several days, then turn on the wheels to dump momentum, repeat until we can upload some permanent fixes.

## Slide 41: Operations – Plan to recover science
A key instrument for GDC, and highest priority for Dellingr operations
Required several weeks of outgassing before turning on high voltage (could not turn on in early mission)
Jan 10, 2018 turned on and verified nominal voltages and currents
Loss of GPS requires software patch to recover INMS science mode
Short Term Solution
Long Term Solution
Use INMS in sun-pointing mode and spin through ram on dayside (requires several uploads)
Use INMS as ram-sensor or run ephemeris propagator on orbit
INMS entrance aperture

## Slide 42: Operations – Uncontrolled Spin Issue
We had a plan for recovering the science
Run the ACS with wheels once per week and run science instruments rest of the time
The satellite entered an uncontrolled spin state by early March
  Spinning at around 120 degrees/second
  ACS designed for 40 degrees/second
By Mid-March
  Communication was terrible
  Spin too fast for particle science
  Bad power numbers
2 minutes of data from March 16th
Magnetic Field
Spin period of 3.4s
Notes: I was spot checking the data and noticed that the wheels seemed to be having no effect.
Robert Burns
Having wheels on makes no difference (so they’re off)
So the mood is dark again. In immortal words of the black knight
Communication was terrible, too fast for particle instrument, bad for power…

## Slide 43: Operations – Bdot
Date | Event
29-Mar – 5-Apr-2018 | B-dot V1 upload
12-Apr – 17-Apr-2018 | B-dot V2 upload
1-May – 7-May-2018 | B-dot V3 upload (attempt 1)
8-May – 15-May-2018 | B-dot V3 upload
Despin via B-dot
Write new B-dot app over ~1 week and test it in the “42” simulation environment
Cadet radio effective upload rate in the order of 16 bps even though actual speed is 9,600 bps
App split into 8 pieces, 181 bytes each
Notes: BDot is a tried and true method for attitude control. relies on the fact that magnetic fields want to align. Carefully time the torquers wrt to background field, and you can control the attidue.

## Slide 44: Operations – De-spinning
3.4s spin
Slow lazy tumble
May 21st - Successful de-spin
1.2 hours
1.2 hours

## Slide 45: Operations – Current Status
Continue to gather INMS science data (still investigating neutral issue)
Upload a software patch to:
  Add diagnostic capability to investigate gyro
  Add diagnostic capability to investigate I2C reset problem
  Fix ACS software reaction wheel eclipse command
Enable sun pointing again if able to isolate I2C reset problem and find a suitable work around
Continue DAGR science if sun pointing mode is enabled again
Technical successes
  Operated DAGR instrument and obtained science data
  Operated INMS ion side and obtained science data
  Completed thermal louver experiment
  Bus operated and continues to operate after 10 months in a limited capacity despite failures, anomalies and challenges

## Slide 46: Operations – Summary of Discussed Challenges
Satellite turned on inside deployer
Noisy Sun Sensor causing jittery pointing performance
Never got good data from IMU
Lost GPS capability before science commissioning
Constant CPU resets (I2C errors)
Uncontrollable spin
Flight software patches uploads

## Slide 47: Operations – Other Challenges
MOC was not planned to handle so many engineering problems
  Mostly setup to update operations parameters and download data
  Used alternate MOC to help streamline the recovery process
  Used ground testing rack to connect to the ground station
Data from radio was deleted twice on-orbit with no apparent reason
Inherent excessive radio bit-flips aggravated on-orbit
  Bit-flips were observed during ground testing
  On-orbit performance is significantly worse
  Data has to be downloaded more than once to fill gaps

## Slide 48: Operations – Lessons Learned
Use a daily reset for failure detection and correction if the concept of operations allows
Maximize the ability to replace flight code on orbit
Make an effort during the development of the software to minimize uploads size
Add as much telemetry as possible and create filter tables to improve the ability to troubleshoot
Consider using redundant components from different sources when having reliability concerns
Plan for longer commissioning period (schedule and staff) in comparison to larger spacecraft
Invest more into ground processing and trending of on-orbit data to identify subtle problems early
Design FDC for handling misbehaving components in addition to failed components
Add flexibility to your software in its ability to reconfigure between different ACS control modes and science instruments
Add hardware diagnostics to the flight software to help isolate problems

## Slide 49: Closing Remarks
CubeSat/SmallSat knowledge gain
  Develop cost/schedule-effective model (culture change)
    Build, Test, Fix and Re-test philosophy
    Used mostly components off-the-shelf
  Develop “lean” & scalable end-to-end systems (processes and hardware)
    Limited formal documentation and CM processes
    Operated in a do-no-harm classification for risk, reviews were not gates
    Stress the "system“ to develop a GSFC CubeSat/Smallsat culture
CubeSat/SmallSat knowledge obtained is shaping our future
  Identify staffing, infrastructure and technology needs
  IRADS, technical equipment and other resources are being used to improve infrastructure and technologies
  Lay groundwork for future missions and proposals (over 10 proposals and 3 won missions)